## Feuille1
	Alexandre (A)	Jonas (JON)	Jostein (JOS)
							start	06/02 (week 6)
	Task	Nb of weeks needed	Start of the task	End of the task	By
UDP	UDP module	1	6	6	JOS
TCP	TCP module	1	7	7			Deadline	12/04 (week 15)
	Interactions with UDP module and event Manager	1	8	8
Event manager	Event Manager	1	9	9
	Watch Dog	1	10	10
	State Machine Elevator	1	11	11
	Driver	1	12	12
	I/O	1	13	13